## Sheet1
Plan for CI/CD Pipeline
Week | Backend | CI/CD | Quality
2023-01-01 | Create GitHub Repo
2023-01-15 | Add python files, MakeFile and requirments
2023-02-01 | Test Github Action | Setup CI Build Server (GitHub Actions) | Build successfully
| Goals | Goals | Goals
| Providing GitHub Repo | Automated CI using GitHub | Test passed
Plan for Setup Azure CLI environment
Week | Backend | CI/CD | Quality
2023-03-01 | Create and activated python environment | No automation
2023-03-15 | Connect with Github repo and pull the project |  | Validate local repo
2023-04-01 | Intializing Azure environment by invoking make all script and run Flask |  | Validate local Env
2023-04-20 | Implement Test locally by invoking make_prediction.sh |  | Validate API tests locally
2023-05-01 | Creating Azure app service
2023-06-15 | Implement Test for web app by invoking make_prediction_azure.sh |  | Validate App locally
| Goals | Goals | Goals
| Azure local Env is Avaliable |  | Azure Local Env is valid
Setup automated CI/CD
Week | Backend | CI/CD | Quality
2023-07-01 | Create Azure DevOps organization
2023-07-10 | Create puplic poject connected to GitHub Repo
2023-07-20 | Create Azure pipeline |  | modify yaml file according our propriet parameters for build and deploy stage
2023-08-01 | Create linux vm as agent contains docker for build and deploy | Setup Cloud-native CI/CD (Azure Pipeline) | VM is ready to be added as agent to Azure pipeline project pool
2023-08-15 | Run pipeline to build , test pulled code from Github repo and deploy artifcate to Azure app using vm as agent
2023-09-10 | Implement testing pipeline by change application name and push to GitHub |  | Validate pipeline
2023-09-20 | Implement load test using locust |  | Validate API after deployment app by pipeline
| Goals | Goals | Goals
| API available on local Azure | CI is automated | Tests passed
| App avaliable on local Azure app sevice | CD is automated
Deployed on Azure
Documentation
Week | Backend | CI/CD | Quality
2023-10-01 | Implement Documentation for CI/CD project by update README.md | No automation | README.md is clear
| Goals | Goals | Goals
| build A-Z help describes project steps |  | Validate Documentation